## BIS-WorkingNotes
Date | Module | Function
2019-11-28 | Datafusion Weightage | Rollback function done
Get status as "Accepted" and the weightage and update in proposed weightage
get Proposed weightage id - using model number and seq=2
Fusion speed list combination of two records for the same model 1. Accepted , 2. drafted or pending
2019-12-12 |  | SBS Meeting in the morning, Start to setup on IBM ICP
Existing System down - setup new system configuration
2019-12-13 |  | Report Backend task
1. Completed 3 more new report backend
2. Peak hours records not showing for edit after rollback
2019-12-16 |  | 1. Empty file genetes on "AccidentAlongExpressway" report
* To fix the above issue - BIS_REPORT_CONFIGURATION table column TEMPLATE_NAME_WITH_PATH - data changed into lowercase
old Record -- 63 -- /ITPT2FileSystem/ITSO/Occ_Planning/AccidentAlongExpressway.rml
updated to Record -- 63 -- /itpt2FileSystem/ITSO/Occ_Planning/AccidentAlongExpressway.rml
update BIS_REPORT_CONFIGURATION set TEMPLATE_NAME_WITH_PATH = '/itpt2FileSystem/ITSO/Occ_Planning/AccidentAlongExpressway.rml' where BIS_REPORT_CONFIGURATION_ID =63
select * from BIS_REPORT_CONFIGURATION where BIS_REPORT_CONFIGURATION_ID =63 ;

## TimeTaken
Date
Work
Time |  | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 |  | Total Hours
Date | 2019-11-27 | 2: SBS First day meeting |  | 4
Date | 2019-11-29 | 9: SBS Work; 11: SBS Second day meeting with CEO; 2: SBS Second day meeting; 6: SBS Work |  | 9
Date | 2019-12-02 | 9: Report Schedule Work; 3: SBS UI discussion with Oscar and Min | SBS Work | 6
Date | 2019-12-03 | 9: Design the SBS UI with Rajesh to get dashboard data manipulation; 3: SBS Second day meeting with CEO |  | 4
Date | 2019-12-04 | 9: Leave
Date | 2019-12-05 | 9: 1. Anomaly Detection Threshold Configuration Rollback Function. 2. Reports (5 nos.) 3. Fusion weights implementation Web services (TIQ) 4. Fusion Weightage column allow 0 value; 2: Design the BIS UI |  | 6
Date | 2019-12-06 | 9: 6. Schedule the report and down load the Report; 2: Discuss with Min and Design the SB UI
| 2019-12-09 | 9: SBS work; 10: SBS UI discussion with Oscar and Min; 2: 1. Bis Work, Anomaly rollback function, Report work |  | 4
Date | 2019-12-10 | 2: 2. Partially done the Free flow calcuation
3. Free flow ave calculation query takes more time, but the response comes quick
Date | 2019-12-10 | 9: Bis Roadname List and File Schedular; 5: Discuss with Min and Design the SB UI |  | 3
Date | 2019-12-11 | 9: Discuss with Min and Design the SB UI; 12: SBS Internal Meeting; 2: BIS
Date | 2019-12-12 | 9: Discuss with Min and Design the SB UI; 11: BIS - IBM ICP; 1: Existing System down - New System Configuration Setup done