## BIS-WorkingNotes
Date | Module | Function
0.88
microsoft bitlocker administratior pin : 135642
2019-11-28 | Datafusion Weightage | Rollback function done
Get status as "Accepted" and the weightage and update in proposed weightage
get Proposed weightage id - using model number and seq=2
Fusion speed list combination of two records for the same model 1. Accepted , 2. drafted or pending
2019-12-12 |  | SBS Meeting in the morning, Start to setup on IBM ICP
Existing System down - setup new system configuration
2019-12-13 |  | Report Backend task
| Report | 1. Completed 3 more new report backend
| Peak Hours | 2. Peak hours records not showing for edit after rollback
2019-12-16 |  | 1. Empty file genetes on "AccidentAlongExpressway" report
| Report | * To fix the above issue - BIS_REPORT_CONFIGURATION table column TEMPLATE_NAME_WITH_PATH - data changed into lowercase |  | Done
old Record -- 63 -- /ITPT2FileSystem/ITSO/Occ_Planning/AccidentAlongExpressway.rml
updated to Record -- 63 -- /itpt2FileSystem/ITSO/Occ_Planning/AccidentAlongExpressway.rml
update BIS_REPORT_CONFIGURATION set TEMPLATE_NAME_WITH_PATH = '/itpt2FileSystem/ITSO/Occ_Planning/AccidentAlongExpressway.rml' where BIS_REPORT_CONFIGURATION_ID =63
select * from BIS_REPORT_CONFIGURATION where BIS_REPORT_CONFIGURATION_ID =63 ;
| Free Flow Speed | Check free flow calculation Speed check | Json input : id:25 proposedEndTime: 20082019 ProposedStartTime: 21072019 | Done
| TIQ Websever call - Fusion Weights Implementation | Fusion weights implementation Web services (TIQ) pg-830
|  | A. for TIQ webserver call, all the 'drafted' status go to COS | Need to changed @Scheduled(cron = "0 54 16 * * ?") | Done
|  | B. API return 'status' along with proposed weight and live weightage - DataFusion Engine Speed |  | Done
2019-12-17 | Fusion weight implementation | Generate correct data in DB for the following model numbers | Model-5s.8 | Done
|  | Table Name : BIS_HIST_FUSED_WEIGHTS_CONFIGURATION | Model-5s.9
|  | Check the model_description and generate corresponding weightage and check the compound weightage for each model number | Model-5s.5
|  | Insert the row | Model-1s.12
| Schedule Report Insert URL | /report-schedule/report-schedule-config/bis-report-schedule-config - insertBisReportScheduleConfiguration() | { | Done | mimeType: "application/vnd.ms-excel",
|  |  | "paramEndTime": "10:50", |  | p_startdate: "20190720",
|  | API Get Call - "reportScheduleTime()" parameter added | "paramStartTime": "09:00", |  | p_enddate: "20190820",
|  |  | "reportName": "DailyPeakHour", |  | p_direction: "1','2",
|  |  | "reportScheduleDate": "2019-12-17 04:12:04.738" |  | p_arterial_corridors: "Outer Ring Road"
|  |  | } |  | reportName: "LTMOverallEMASArterialReports"
p_roadname : “Outer Ring Road”
| Example Report Parameter |  | p_direction:”1','2” |  | mimeType: "application/vnd.ms-excel"
|  |  | p_endate:20190808 |  | p_typeacc: "ASSIST_MOVEOFF"
|  |  | p_startdate:20190720 |  | p_startMM: "201907"
|  |  | reportName: "AllAccidentandBreakdownDetailsforEMASArterial" |  | reportName: "AccidentAlongExpressway"
| To generate report file and stored in to local directory | /report-schedule/report-schedule-config/bis-report-schedule-config getBisReportScheduleConfigurationById() |  | Done
Table Name : BIS_REPORT_SCHEDULE_CONFIGURATION
Report Generate Parameter - starttime, endtime, report name, mimetype
2019-12-18 | Docker Desktop Installation | 1. Signup in docker hub
2. Login with office id, but I didn’t get the verification email
3. I tried with personal Id
4. Downlaod docker desktop for windows
5. insall the docker, restart two times to set the VM
6. IBM-ICP introducation meeting (2 hrs)
7. Install and Setup kubernate, helm, linux
8. Create certificate
2019-12-19 |  | 1. Fixing Free flow speed - calculated and defualt, changed in query
2. setup testing environment
3. IBM ICP configuration setup
4. 3 hrs - he spend 20 minuts todo initial setup
2019-12-20 |  | Leave
2019-12-23 | Testing Error | error : Report file generated empty | issue is in url - point to old url | Done
one parameter is missing from the old url
|  | 2019-12-23 10:56:51.030 INFO [bis-services,,,] 2216 --- [pool-7-thread-1] | Directed to Correct url - Report works fine
sg.com.ssa.itpt2.service.BisElixirReportConfigurationServiceImpl.callToElixirServer - X-elxjob.Exception: java.lang.IllegalArgumentException Empty mime type
| IBM ICP | Docker image created, - run the docker image - its running | Doing
heml chart is created
|  | value.yml, deployment.yml and service.yml file also modified | ssl: |  | ssl:
|  | log shows the server is working and no error | key-store: classpath:wildcard.bis.itpt.its.com.p12 |  | key-store: classpath:bis.itpt.its.com.p12
|  | now created the certificate for unique url | key-store-password: biscertpass |  | key-store-password: biscertpass
|  | update with application.yml file | key-store-type: PKCS12 |  | key-store-type: PKCS12
|  | trying 2 hrs - he spend 20 minuts | no figure out the solution |  | key-password: biscertpass
key-alias: bis.itpt.its.com
2019-12-24 | Backend - eqipmentid-roadname | equipment id and road name data from backend through a GET request |  | Done
/bis-elixir-report-eqiproadname - getEqipmentRoadNamesForReport()
| IBM ICP | SSL Certificate and
2019-12-26 |  | ITSO (OCC Ops) Report - Traffic alert log (STM) | Task-BIS-032 - Done | Done
Data Fusion Volume Ranking
TIQ WebService call
2019-12-31 | IBM ICP | SSL Certificate and | Using Local Certificate | Done
2020-01-01 | free flow speed query need to change | (-140) query -
2020-01-02 | Sonar - Junit | Sonar and Junit partically done |  | Done
2020-01-03 | Junit and Jacoco | Jacoco Setup, junit test case |  | Done
|  | ICP certificate used with Originally certificate | Local Setup done | Done
2020-01-06 | ICP | ICP certificate used with Tian he certificate (backend) | IBM container setup | Done
Report schedular setup
|  | Frontend | partically done
Facing issue, server location not found
2020-01-08 |  | backend done https with single cetificate |  | Done
2020-01-08 |  | HTTP to HTTPS - ICP IBM setup with chain certificate |  | Done
Frontend and backend
2020-01-09 |  | elixir.server.url : http://10.180.11.133:8080/elx/do/eno/re | URL point to http, but the reponse is https
So report not generated
if I change the elixr url to https SSLException error is throwing
| writing junit test case | Anomaly Detection
Fusion weightage
Peak hours
Free flow speed
| Volume Ranking | Get all volume Ranking
Edit Single Volume Ranking
Insert new volume
2020-01-10 | Elixir Report Error | Fixing the Report generation error | Reason the report generated and stored into the localfolder instead return to the browser | Done
The error message was Inputstream closed
1. Report Parameter Added
2. Frontend change deployment 3 times
3. R1-status xl file updated
2020-01-13 |  | Report parameter backend API
| BIS UI | Deploy BIS frontend in ICP IBM
| TIQ WebServer Calls | Fusion weightage | BIS_HIST_FUSED_WEIGHTS_CONFIGURATION
|  | Anomaly Threshold Configuration | BIS_ANOMALY_DETECTION_THRESHOLD_CONFIGURATION
| install COS certificate | https://www.thewindowsclub.com/manage-trusted-root-certificates-windows
using console Root Certificate
2020-01-14 | BIS UI | Deploy BIS frontend in ICP IBM
Insert records in "BIS_ANOMALY_DETECTION_THRESHOLD_CONFIGURATION" Table
EMAS, EA, KPE_MCE, TCS, TS, GLIDE, ST, ERP2, ERP - generate new records for these Data Sources
2020-01-16 | Report Parameter | Generate Report Parameter output
Testing TIQ web server call
Report Scheduler - calling the table every seconds
Two API added to retrieve the Road name
2020-01-17 | Peak Hours Rollback | GET/sysconfig/peak-hours-configuration/rollback-bis-peak-hours-configuration
rollbackBisPeakHoursConfigurationById
| Free Flow Rollback | /sysconfig/free-flow-speed/rollback-bis-free-flow-speed
rollbackBisFreeFlowSpeedById
| Fusion Weightage Rollback | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf-rollback
bisHistFusedProposedWeightRollbackUpdateById
Fusion Weightage record changed
Datasource ST,TS,ERP, VAS - TS_weightage is missing,
I updated the corresponding record

## TODO
TODO Task
1. Data Fusion Volumn/data source /rank - new table creation | A. Insert / View / Rollback
SELECT e.external_system_id,e.external_system_name, r.ranking FROM data_fusion_volume_ranking r, external_system e WHERE e.external_system_id = r.external_system_id;
B. Rollback return "liveWeights": "EMAS = 0.2, TS = 0.8, ERP2 = 0.9, VAS = 1.0 ",
C. TIQ call
3. Report schedule | Report Schedule Trigger - read the time and generate the report
Server Folder location - to store schedule report files
What is the Report Name - Standard or common
rollback - meta data
General - Unusual Congestion - Task-BIS-243
General - Data Quality Checks (to send email when data quality drops below certain threshold) - Task-BIS-241
port mapping
diattachmode
docker compose
Here is the queries:
select distinct B.EQUIPMENT_ID, A.EWAY_NAME as eway name from EWAY_KM_LINK_MAPPING A, EMAS_EQUIPMENT_MAPPING B
WHERE A.LINK_ID =B.LINK_ID ;
Edit Consistency Cluster Threshold | task-BIS-245 | 10%
jacoco code coverage
COS Hitlab location | cos/cos-coms.default-library/deployment
cos/cos-coms.default-library/src/main/resources

## TimeTaken
Date
Work
Time |  | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 |  | Total Hours
Date | 2019-11-27 | 2: SBS First day meeting |  | 4
Date | 2019-11-29 | 9: SBS Work; 11: SBS Second day meeting with CEO; 2: SBS Second day meeting; 6: SBS Work |  | 9
Date | 2019-12-02 | 9: Report Schedule Work; 3: SBS UI discussion with Oscar and Min | SBS Work | 6
Date | 2019-12-03 | 9: Design the SBS UI with Rajesh to get dashboard data manipulation; 3: SBS Second day meeting with CEO |  | 4
Date | 2019-12-04 | 9: Leave
Date | 2019-12-05 | 9: 1. Anomaly Detection Threshold Configuration Rollback Function. 2. Reports (5 nos.) 3. Fusion weights implementation Web services (TIQ) 4. Fusion Weightage column allow 0 value; 2: Design the BIS UI |  | 6
Date | 2019-12-06 | 9: 6. Schedule the report and down load the Report; 2: Discuss with Min and Design the SB UI
| 2019-12-09 | 9: SBS work; 10: SBS UI discussion with Oscar and Min; 2: 1. Bis Work, Anomaly rollback function, Report work |  | 4
Date | 2019-12-10 | 2: 2. Partially done the Free flow calcuation
3. Free flow ave calculation query takes more time, but the response comes quick
Date | 2019-12-10 | 9: Bis Roadname List and File Schedular; 5: Discuss with Min and Design the SB UI |  | 3
Date | 2019-12-11 | 9: Discuss with Min and Design the SB UI; 12: SBS Internal Meeting; 2: BIS
Date | 2019-12-12 | 9: Discuss with Min and Design the SB UI; 11: BIS - IBM ICP; 1: Existing System down - New System Configuration Setup done

## Report Parameter
p_startMM: "201907"
p_typeacc: "ASSIST_MOVEOFF"
mimeType: "application/vnd.ms-excel"
reportName: "AccidentAlongExpressway"
mimeType: "application/vnd.ms-excel",
p_startdate: "20190720",
p_enddate: "20190820",
p_direction: "1','2",
p_arterial_corridors: "Outer Ring Road"
reportName: "LTMOverallEMASArterialReports"

## Sheet1
Sl. No | Particulars | Name | Query
Data Fusion
1 | Data Fusion Flow (GET Request) from the view Show all data fusion | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf-fusion-model-Speed - bisHistFusedWeightAndFusionModelSpeed() | Call the View VW_BIS_DATA_FUSION_ENGINE
2 | Get one records for edit only show particular weightage (GET Request) | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf-fusion-model-by-id - bisHistFusedProposedWeightEditById()
3 | Update the single recordweightage (PUT Request) | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf - bisHistFusedProposedWeightUpdateById() | if status pending - no record inserted - error thrown
if no status - then new record inserted with drafted status
if status accepted - new record inserted with drafted status
4 | Update status (PUT Request) | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf-fusion-model-status - bisHistFusedProposedWeightProposedWeightStatus() | update the "Pending" status with exisiting record
5 | View record history (GET Request) | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf - bisHistFusedWeightConfigurationHistoricalView() | status accepted latest records showns
6 | record roll back (PUT Request) | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf-rollback - bisHistFusedProposedWeightRollbackUpdateById() | New record created with existing status, weightage, holidays for the particular model
7 | WebServer call TIQ (GET Request) | /bis/bis-hist-fused-weight-confi/bis-hist-fused-weight-conf-rollback - bisHistFusedProposedWeightRollbackUpdateById() | Drafted Status records report transfer to TIQ
8 | Pending Update Multiple drafted status to pending
Free flow Speed
1 | all free flow speed (GET Request) | /sysconfig/free-flow-speed/active-bis-free-flow-speeds - getAllActiveBisFreeFlowSpeed() | Table - ROAD_CATEGORY_CODE, Table - BIS_FREE_FLOW_SPEED
2 | Free flow speed one record (GET Requst) | /sysconfig/free-flow-speed/bis-free-flow-speed - getBisFreeFlowSpeedById() | Get Singel Record using two tables
3 | Insert a record (POST Request) | /sysconfig/free-flow-speed/bis-free-flow-speed - submitBisFreeFlowSpeed() | New record insert in Table - BIS_FREE_FLOW_SPEED
4 | latest records (GET Request) | /sysconfig/free-flow-speed/bis-free-flow-speed-change-history - getChangeHistoryForBisFreeFlowSpeed() | Table - ROAD_CATEGORY_CODE, Table - BIS_FREE_FLOW_SPEED
5 | Rollback id (POST Request) | /sysconfig/free-flow-speed/rollback-bis-free-flow-speed - rollbackBisFreeFlowSpeedById() | New record inserted with existing value, Table - BIS_FREE_FLOW_SPEED
6 | Calculated free flow speed (GET Request) | /sysconfig/free-flow-speed/bis-free-flow-calculated-speed - getCalculatedBisFreeFlowSpeed() | parameter - id, proposed starttime, proposed endtime to get response Table - HIST_LINK_DATA_ITPT1, Table - VW_GIS_LINK_VIEW
7 | Default free flow speed (GET Request) | /sysconfig/free-flow-speed/bis-free-flow-default-speed - getDefaultBisFreeFlowSpeed() | parameter - id, to get response Table - HIST_LINK_DATA_ITPT1, Table - VW_GIS_LINK_VIEW
Peak-hours-configuration-controller
1 | All peak hours data (GET Request) | /sysconfig/peak-hours-configuration/active-bis-peak-hours-configurations - getAllActiveBisPeakHoursConfiguration() | Table - BIS_PEAK_TIME
2 | To get pariticular Recored (GET Request) | /sysconfig/peak-hours-configuration/bis-peak-hours-configuration - getBisPeakHoursConfigurationById() | parameter - id, to get particular record
3 | To get pariticular Recored (GET Request) - user type | /sysconfig/peak-hours-configuration/bis-peak-hours-configuration-by-userType - getBisPeakHoursConfigurationById() | parameter - usertype, to get particular records
4 | To submit record (POST Request) | /sysconfig/peak-hours-configuration/bis-peak-hours-configuration - submitBisPeakHoursConfiguration() | New record inserted
5 | History records (GET Request) | /sysconfig/peak-hours-configuration/bis-peak-hours-configuration-change-history - getChangeHistoryForBisPeakHoursConfiguration() | Paremetet - id, internally pass usertype, peaktype
6 | Roll back (GET Request) | /sysconfig/peak-hours-configuration/rollback-bis-peak-hours-configuration - rollbackBisPeakHoursConfigurationById() | Parameter id, remark, New record inserted with remarks
anomaly-detection-threshold-config-controller
1 | All records (GET Request) | /sysconfig/anomaly-detection-threshold-config/active-bis-anomaly-detection-threshold-configs - getAllActiveBisAnomalyDetectionThresholdConfig() | Table - BIS_ANOMALY_DETECTION_THRESHOLD_CONFIGURATION
Parameter - id
2 | Get Particular records (GET Request) | /sysconfig/anomaly-detection-threshold-config/bis-anomaly-detection-threshold-config - getAnomalyDetectionThresholdConfigById()
3 | Submit new record (POST Request) | /sysconfig/anomaly-detection-threshold-config/bis-anomaly-detection-threshold-config - submitAnomalyDetectionThresholdConfig() | Insert new record
4 | Change history (GET Request) | /sysconfig/anomaly-detection-threshold-config/bis-anomaly-detection-threshold-config-change-history - getChangeHistoryForBisAnomalyDetectionThresholdConfig()
5 | Many record inserted (POST Request) | /sysconfig/anomaly-detection-threshold-config/bis-anomaly-detection-threshold-config-many - submitManyAnomalyDetectionThresholdConfig() | Many record submitted with all values
6 | Remark updated when you roll back (POST Request) | /sysconfig/anomaly-detection-threshold-config/rollback-bis-anomaly-detection-threshold-config - rollbackBisAnomalyDetectionThresholdConfigById() | parameter - id, remarks, new record inseted using exisiting values

## Error
Changes | Error
Mention Certificate in application.yml file | 2019-12-31 11:13:07.026 ERROR [bis-services,,,] 16296 --- [restartedMain] org.apache.catalina.util.LifecycleBase.log - Failed to start component [Connector[HTTP/1.1-8888]]
org.apache.catalina.LifecycleException: Protocol handler start failed
openssl pkcs12 -export -in bis.itpt.its.com.cert.pem -inkey bis.itpt.its.com.key -out bis.itpt.its.com.p12 -passin pass:bis -passout pass:bis -name bis
Export cert to pkcs12 file
Use cert key and cert.perm file names
#key-store-password: pass123
#key-store: classpath:mykeystore.jks
TIQ Call Error
Jacoco
Jacoco Facing issue | The default junit test folder not present the project
Test folder Created manually, Add junit plugin
create the junit test case file
setup Jacoco and Sonar
The problem is jacoco exec file not created automatically - so can't see the coverage information
surefire-reports folder not created
Front end ICP setup
Report Error Exception
After intstalling root certificate in java