## Screens
TT231 Demo Project Screen Details
Modules | Screen | Sub Screens | Screen Description | Reference Document | Figure | Notes | Doubt
Login | Login Screen |  | Username and password to login into the system | 3.1.1 Login In (1) | Figure 3.4 | Login validation not include
Login | Zone Selection Screen |  | select the zone | 3.1.1 Login In (2) | Figure 3.5 | validation not include
Common Control (C2) | Incident Records Display page | Incident Record | List all Incident records | 3.1.2.1 Incident Record | Figure 3.7 | validation not include
Common Control (C2) | Incident Records Display page | Menu Icon | Display the list of menu's - based on the menu selection corresponding window will open | 3.1.2.1 Incident Record | Figure 3.7
Common Control (C2) |  | Work Order | Display List of workorder and graph | 3.1.2.1 Incident Record | Figure 3.8 | validation not include
Common Control (C2) |  | Technical Alarm | Display with List of record and graph | 3.1.2.1 Incident Record | Figure 3.9 | validation not include
Common Control (C2) |  | Environmental Monitoring | List all EM records | 3.1.2.1 Incident Record | Figure 3.10 | validation not include
Common Control (C2) |  | Road Work | List of Road Work records | 3.1.2.1 Incident Record | Page 25 | validation not include
Common Control (C2) |  | Event | List of Event | 3.1.2.1 Incident Record | Page 26 | validation not include
Common Control (C2) | IR Filter and Layout | Incident Record | List the records based the the search or filter | 3.1.2.2 Panel Filtering & Layout Customization (1) | Figure 3.11 | validation not include
Common Control (C2) | Merge the panel | IR / EM / WO / TA | Merge the panel two or three | 3.1.2.2 Merge Panel (2) | Figure 3.12, Figure 3.13 | validation not include
| Split the Panel | IR / EM / WO / TA | Split the panel into two or three | 3.1.2.2 Merge Panel (3) | Figure 3.14, Figure 3.15 | validation not include
| Notification Panel | Technical Alarm | Notification display | 3.1.2.3 Notification | Figure 3.16 | validation not include | required Technical Alam insertion screen
| Notification Panel | Technical Alarm | Return to previous TA page |  | Figure 3.17 | Back to the previous screen
BIS Real-time |  |  |  | 3.1.3.2 Selecting a pre-created template |  |  | Need more details 1. Sample Data 2. the data from IR/WO/TA/EA
GIS MAP | Right Click menu display backgroud Road map | Menu Iist of IR | Show all the IR | 3.1.4 Incident Record (IR) workflow (1) | figure 3.25
| New IR Creation Screen | Create IR | To create a new IR and fill all the details | 3.1.4 Incident Record (IR) workflow (2) | figure 3.26 | validation not include
| If New IR is heavy traffic | To draw a line | Show the heavy traffic lane | 3.1.4 Incident Record (IR) workflow (3) | figure 3.27 |  | No to check
| To Lane Block and Unblock | Add new link | show the lanes | 3.1.4 Incident Record (IR) workflow (4) | figure 3.28
| Add New Lane | List the lane position where to add | show the lanes | 3.1.4 Incident Record (IR) workflow (5) | figure 3.29
| Delete the existing Lane | List the lane | Show the lanes | 3.1.4 Incident Record (IR) workflow (6) | figure 3.30
| IR Creation Done | Create to Move Response Screen | Create Tab and Response Tab is added |  | figure 3.31 |  | No to check
|  | Create to Move Response Screen | Response tab (which contain VMS Message Page) |  | figure 3.32 |  | No to check
| Add Equipment to Plan | Menu to add a new plan | Need to complete from Page 40 to 77 - ref word document | 3.1.4 Incident Record (IR) workflow (8) | Figure 3.33
| Multi Select VMS Plans |  | To select mulitple VMS | 3.1.4 Incident Record (IR) workflow (9) | Figure 3.34
Todo Page 40
Note on E3: Referred Document TT231_Storyboard_VA.05.doc
Note on F3: Referred Document TT231_Storyboard_VA.05.doc

## Setup
Software Setup
Column1
Create key screens using a normal white background theme
HTML5/Bootstrap/AngularJS/JSON technologies

## Development Pg Info
Panel | Screen Info | File Name | Status | Steps | URL
Login | Login Screen | login.html | done
| zone selection screen | zoneselection1.jsp | done
CC2 | common control 2 (cc2) | ccgridview.jsp | doing | 1. Create 5 files with different no. of records and push different files in different timing.
2. Remove 'Over' status from the Incident
3. Create 5 different chart data and change it accordingly
4. Work Order remove "Overdue work" from work order
5. Display different incident in each panel
Pending Task :
Progress bar
Graph animation
BIS
BIS Work Station and BIS Desktop | D3Js.com |  | Task todo | 1. Speed Line graph (line Chart) - both direction
follow BIS WorkStation |  |  |  | X - Speed data (50, 100)
Y - Kilo meter (24,25,26)
2. Road Work - Bar Chart
X - no of roadwork
Y - display major road (Expressway, Aye, CTE etc.,)
GIS |  |  |  | 1. Confiture arcGIS setup locally
2. download all libraries
3. deploy it in server
4. Use the url to get the functionality
5. but u need to call it with url
MRT Incident |  | createmrtwin.jsp | Main File | 1. MRT breakdown selection page | http://localhost:8080/DemoTrans/createmrtwin.jsp
CreateMRTIncident |  | mrtmap.css | map layer property css code | 2. draw line on the map mrt breakdowns
|  | mrtmap.js | Map layer function Java Script file | 3. ArcGis base map used
|  | trainy.png | Train image file
|  | roadmap.jpg | static map image
|  | mrtinc.css | UI layer - side panel display css | MRT Create incident left display Menu
|  | cctv.png | cctv camera image | Image file for the mrt selection stations (first page)
|  | roadwork1.jpg | roadwork image
Incident |  | createirwin1.jsp |  | Map and MRT line selection
|  | mrtinc.css | UI layer - side panel display css
|  | mrtmap.css | map layer property css code
|  | irmap.js | UI layer - side panel display css
Event |  | createventwin.jsp |  | Event creation
|  | mrtinc.css | UI layer - side panel display css
|  | mrtmap.css | map layer property css code | Step to add "VMS msg inside Div" on map
|  | eventmap.js | Map layer function Java Script file | 1. add one row in datapenal column jsp and div tag on the map column- createventwin.jsp
|  | democontroller.js |  | 2. create div in css - mrtmap.css
3. write js function - eventmap.js
4. write vms message in - democontroller.js

## lati-logi
Longitude | Latitude |  |  | Location MRT | use this file to get latitude and longitude info
103.839 | 1.281 |  |  | MRT - Outram Park | file:///C:/GisMap/popupinmap.html
103.817 | 1.289 |  |  | MRT - Redhill
103.806 | 1.294 |  |  | MRT - Queenstown
103.79 | 1.307 |  |  | North Buona Vista Road, Singapore
103.778 | 1.312 |  |  | MRT-Dover
CCTV Camera
103.859, 1.337 Toa Payoh
103.884 | 1.358 |  |  | Serangoon
103.851 | 1.373 |  |  | Ang Mo Kio
103.898, 1.372 Hougang
103.925, 1.336 Bedok
103.957, 1.345 simei
103.902, 1.323 Eunos
103.839 | 1.281 |  |  | MRT - Outram Park
103.817 | 1.289 |  |  | MRT - Redhill
103.806 | 1.294 |  |  | MRT - Queenstown
103.846, 1.322
103.86, 1.317
Road Work
103.898, 1.372 Hougang
103.925, 1.336 Bedok
103.957, 1.345 simei
103.902, 1.323 Eunos
103.79 | 1.307 |  |  | North Buona Vista Road, Singapore
103.778 | 1.312 |  |  | MRT-Dover
103.84, 1.329
103.85, 1.327
103.51'13.892 | 1°19'53.287" |  |  | Lorong 6 Toa Payoh approaching Braddell Road;
103°51'1.225" | "1°20'25.973" |  |  | Lorong 1 Toa Payoh approaching Braddell Road
1.3325 | 103.8615 |  |  | Un know name
1.3319 | 103.8622 |  |  | Whampoa Flyover,
PIE 1.329576 | 103.8579 |  |  | PIE
103.8575 | 1.3692 |  | , | Ang mo kio CTE
103.8582 | 1.3838
103.8554 | 1.3759
103.8584 | 1.3615
Accident IR CTE
x | 30451.9920839 | 103.8554 | 1
y | 39770.1588305 | 1.3759
x | 31328.9208527 | 103.8632 | 2
y | 39969.9459666 | 1.3777
x | 31499.1505488 | 103.8648 | 3
y | 39170.2856139 | 1.3705
x | 30690.9924681 | 103.8575 | 4
y | 39019.5417418 | 1.3692
x | 30881.1094603 | 103.8592 | 5
y | 38314.5195971 | 1.3628
x | 30790.9181002 | 103.8584 | 6
y | 38176.531181 | 1.3615
x | 30767.9157962 | 103.8582 | 7
y | 40638.2173913 | 1.3838
x | 30799.8271562 | 103.8585 | 8
y | 40835.2468955 | 1.3856
VMS Ids | Location
tcttp_713023 - at 138m east/Ang Mo Kio Ave5
tcttp_713028 - at 222m west/Ang Mo Kio Ave 5
tcttp_713026 - at 205m west/Ang Mo Kio Ave 3
tcttp_713021 - at 170m east/Ang Mo Kio Ave 3
tatip_711021 - CTE towards AYE
tatip_711020 - CTE towards SLE
tatip_711022 - CTE Towards SLE / LP34 /14.66
tatip_711023 - CTE towards AYE
Traffic Light Info
1471
31088.9 | 103.8610747°
39920.08 | 1.3772975°
426
30755.81 | 103.8580815°
39822.02 | 1.3764106°
1270
30383.93 | 103.8547399°
39757.74 | 1.3758293°
CCTV Camera Location
eqt_id - sapsc_719085, sapsc_719084, sapsc_719082
30832.0437 | 103.8587667
39694.079 | 1.3752537
30777.5945 | 103.8582773
39888.6793 | 1.3770134
30799.5271 | 103.8584744
39978.57 | 1.3778264

## <DIV> notes
Step to add "VMS msg inside Div" on map
1. add one row in datapenal column jsp and div tag on the map column-
createventwin.jsp
mrtmap.css
map div, vms message div available
eventmap.js
(All event related javascrip available to display on the map)
democontroller.js
ng-model message
mrtinc.css
All UI panel display css available - like button, textarea etc

## Graph
change the graph type

## GIS
Layer | FileName | Usage
WMSLayer - | loadwms2.html | Load VMS img using geoserver on the map using wmslayer form arcgis api
WMTS Layer – | localmapzoom.html | Load base map using openmaptile server map and use wmts layer from arcgis api
copy "WMSLayerInfo.js" from 3.28\esri\layers to 4.11\esri\layers
PTV Optima: 3 Steps Towards Real Time Traffic Management
https://www.youtube.com/watch?v=t5h8R61Gdzc

## Daily Work Status
Date | Particulars
12/2 - 15/2 | Software Installation | Install java, eclipse, Maven, tomcat and write a sample program.
Study bootstrap and created some samples.
Got project document. Yet to understand.
17/2 - 21/2 |  | Did Angular js example and idea from the demo project. Got folder access.
Got new laptop in the afternoon.
24/2 - 1/3 |  | Back to office around 2pm.
New laptop setup, installed jdk, maven,tomcat,eclipse, github desktop.
• JSON object insertion and deletion using angularjs
• JSON page for zone selection
• Gave short Demo to Ibrahim and Chee Sung
• Afternoon went to LTA - ITSC - Get to know real time application.
Create popup windows to create IR. Returned old laptop
4/3 - 8/3 |  | Modify the table content and create Drop down box to create IR.
And add Stat time to corresponding text box.
• Add scroll bars with tables
• Separate the CSS file for incident and events.
• Date and Time picker added
11/3 - 15/3
18/3 - 22/3 |  | Tuesday went to Mountbatten Office.
Work on page display design
Met Chiann chiann
Working in MRT breakdown scenario
Went to Fort canning to see the IR work flow
25/3 - 29/3 |  | Show a Demo to Chiann Chiann
She gave Demo some color change in text box and table design,
1.change the search bar to gray
2.Double color (light and dark) background.
3.Event table need to change bigger size.
4.All buttons are same size in a table.
5.Highlights the cursor pointer row.
6.Table alignment change
Wenr to Mountbatten to get info about GIS and BIS
Table design and side panel display in events
1/4 - 5/4 |  | Got Css from Aaron, changed checkboxes in zone selection, zone and login page changed as per model.
Partially completed on MRT, Incident, event creation,
Login and zone selection done.
Google map example is done.
Working on incident creation module, search bar icon and dropdown icon change.
8/4 - 12/4 |  | First phase Demo 1
Get feedback more work on map.
Met Sela to get GIS detail
Work on GIS Map
15/4 - 19/4 | GIS Integration part | Work on ArcGIS api,
22/4 - 26/4 |  | Integrate map with UI
29/4 - 2/5 |  | Base map setup, geo server setup
6/5 - 10/5 |  | configure geo sever with baseMap
13/5 - 17/5 |  | configure WMST layer and WMS layer with Arcgis ApI 3.48
20/5 - 24/5 |  | configure WMST layer and WMS layer with Arcgis ApI 4.11
27/5 - 31/5 |  | Intial map Zooming level
convert xy to longitude and latitude
configure map with windows UI panel
HTML table format and DIV format not support to load the map on windows UL panel
changed to DIV panel tag to load the map inside the windows UI panel
MRT breakdwonk point and layer display - getting lati and logi from google maps
Mobile road work point and layer display -
Layer configure in geo server VMS/ MRT stations/ MRT Line/ carriageway / VMS / CCTV heavy traffic
implement in arcgis api to locate the layer and
Convery text box to context text box to show the image
Change zoom to that location
Draw continues line near the lane
3/6 - 7/6 | Accident | map has to show traffic closed lane in red, normal traffic in green, and the traffic jam in orange
Choosing CTE road to draw a lane
Finding lane distance to draw a line
QGIS application installed to get the geometroic points
BIS part partially started
17/6 - 21/6 | Modify the Accident Form | Adding direction, startpoint endpoint, congestion point
Video display to Image display and drag to everywhere
Removbe video display to image display
| New Assignment | Prediction - show 3 modal to choose one scenario based selection time, the scenario time change and the geo points show on the map and correspoding popup window come with text and image
Action plan new modal window
Action plan inner new modal window
poptemplate image and text added using <SVG> tag - Scalable visuvalize graphics
VMS points Symbology changed, imaged changed so cut individual image and transparent and rename it then resize image and published in geo server
24/6 - 28/6 |  | Scenario 1 and scenario 2 json and correspoinding model added
8 vms eqipment xy point to lati and logi points
Canning Msg taken from the onemotoring website
OBU alert message got it from Min
| New layer added for Traffic light to show Glide Data | Glide layer and in geoserver and postgres and arcgis api
Bis bar chart and Doughnut Chart
Traffic light - Glide message added and display on the map
Change the C2 font color style, alignment, change chart
1/7 - 5/7 | To create congestion
linear referencing
Speed data,create a new table with exisining carriageway table and added speed data column
import speed data from csv. Create a new table without link_id duplicate with speed
copy the speed column to new table
The csv Speed data file is not import proberly
some of the speed band data is missing
arterial and expressway speed band needed to create a layer
Based on the above speed band the new data has to be inserted
new table created with speed column
new Speed Link layer created with Red, Amber, Green color
segmentation - lane has to show 3 color red, amber, green
Get Multiple longitude and latitude from googlemaps
draw the color to certain point red and draw the color certain point to green, draw the color certain point to amber
For traffic prediction 3 layer has tobe desinged with different range of color combination.
set the interval to call the each and every layer.
if call the new layer, existing layer has to be deleted.
8/7 - 12/7 |  | BIS Part - Speed data chart, Incident data Chart
| Working on LTA Feedback | Zone selection page removed, Login and command control page linked
Change the font color in command control
Draw prediction on map after creating accident
Camera Points added on the map
Video generated based on the camera
new traffic speed layer added near the accident location
bis module json file added
changing the bis format as per new ppt (Infographics_conclusion_v5 (with comments))

## Issue facing
Facing Issue
1. Using arcgis 3.28 API to zoom the basemap, to required level, scale, resolution values - trying to find out.
2. wms layer working in arcgis 3.28 but the layer shows the image in different place on the map.
2. Zoom in basemap using arcgis 4.11 - wokring fine, but wms layer not working in this version.
3. Facing Map alignment problem
map has to come screen left side, but it will not fit with table, layer,
trying with <div> tag
4. arcgis api 3.28 code is different from arcgis api 4.11
5. I change accordingly.
Speed Data csv not not generating a new table.
some error in extracted data. I modify the speed data csv file
update the exiting
cat1 - Expressway >10 and <20 - red
cat2 - Major Arterial >20 to <40 - red
cat3 - minor arterial
cat4 - Local access
cat5 - Slip Road
cat7 - Non-Category
cat8 - Short Tunnel (ST)
10-20 Arterial road - Red
20 - 40 expressway - Red
21 - 40 arterial road - amber
41 - 60 express - amber
>40 arterial road - green
>60 expressway - green
#006400 - dark green
#ffbf00 - amber
#FF0000 - red
#8b0000 - Dark Red
#00FF00 - Green
75,175,198 - blue
192,80,77 - brown
155,187,89 - green
128,100,162 - lavender
79,129,189 - dark blue
0,176,80 - green
192,0,0 - red
255, 192, 0 - yellow
#ffffff - white
#000000 - Black
219,132,61 - brown
170, 70, 67 - burgundy